## Instructions
The template includes four spreadsheets:
1. | Cost Estimate: Estimate the project cost based on WBS items
2. | Labor Estimate - Software Dev: Two different approaches to estimating lobor cost of software development
3. | EV Analysis: Monitor the project progress ans staus by calcuclating the schedule and cost performance indicators
4. | EV Chart: Demostrate the project status in terms of schedule and cost (updated automatically based on the data in "EV Analysis") | , input the "# Units/Hrs." and "Cost/Unit/Hr." columns to estimate the cost for each WBS item.
Using this template, you need to do
1. Replace the WBS item list in "Cost Estimate" and "EV Analysis" with the WBS item list of your own project
2. In "Cost Estimate":
2.1 Input the "# Units/Hrs." and "Cost/Unit/Hr." columns to estimate the cost for each WBS item.
2.2 Update the formulas of subtatal and percentage calcuations based on your own WBS item list
2.3 For the cost of "Software development", use the "Labor Estimate - Software Dev" to decompse and estimate the cost
3. In "EV Analysis":
3.1 For each WBS item, allocate the cost estimated in "Cost Estimate" to the corresponding month(s) when the cost occurs
3.2 Determine the month as the time point for evaluate the project status, such as May 31 in the template
3.3 Input hypothetical numbers in the rows of "Monthly Planned Value (PV)", "Monthly Actual Cost (AC)", and "Monthly Earned Value (EV)" from the beginning month to the month you determine in the Step 3.2
3.4 Update the formulas in the rows of "Cumulative Planned Value (PV)", "Cumulative Actual Cost (AC)", and "Cumulative Earned Value (EV)" to calculate the ccumulative numbers based on the inputs in Step 3.3
3.5 Check the formulas of CV, SV, CPI, SPI, EAC, and "Estimated time to complete" and update them if necessary to see whether these indicators are calculated correctly
4. In "EV Chart", check whether the chart has been updated automatically based on the data in "EV Analysis"

## Cost Estimate Analysis
Smart Parking Management Project Cost Estimate
Prepared by:All task no Chill | Date: | 2025-03-07
Note: Change the WBS items and other entries to meet your project needs. This data is from Figure 7-1 of Schwalbe's text
Information Technology Project Management, Fourth Edition. Also make sure the formulas work properly based on the data you enter.
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Project Initiation and Management |  |  |  | 28200 | 11.23%
1.1 Define the project Scope and objectives | 40 | 100 | 4000
1.2 Identify stakeholders
1.2.1 Market analysis | 30 | 90 | 2700
1.2.2 User Survey | 30 | 90 | 2700
1.3 Identify Key Risk Indicators | 36 | 100 | 3600
1.4 Develop initial project timeline | 36 | 100 | 3600
1.5 Establish project governance structure | 40 | 100 | 4000
1.6 Define risk management plan | 40 | 90 | 3600
1.7 Develop resource allocation | 40 | 100 | 4000
2. System Design |  |  |  | 49670 | 19.78%
2.1 Define system requirements
2.1.1 Identify and document functional requirements | 30 | 90 | 2700
2.1.2 Identify and document non-functional requirements | 30 | 90 | 2700
2.1.3 Validate requirements with stakeholders | 25 | 100 | 2500
2.2 Design database schema
2.2.1 Identify required data entities and relationships | 25 | 95 | 2375
2.2.2 Design an entity–relationship diagram | 25 | 95 | 2375
2.2.3 Choose the database technology | 18 | 95 | 1710
2.3 Create system architecture diagram | 40 | 100 | 4000
2.4 API design | 84 | 100 | 8400
2.5 Security and Authentication
2.5.1 Implement user authentication | 36 | 100 | 3600
2.5.2 Apply data encryption | 24 | 100 | 2400
2.5.3 Establish disaster recovery and backup strategies | 24 | 100 | 2400
2.6 AI Model Development for parking
2.6.1 Define AI use cases | 35 | 110 | 3850
2.6.2 Collect and clean historical parking data | 32 | 110 | 3520
2.7 Integration with payment gateway | 24 | 110 | 2640
2.0a Database & Design Tool Licenses |  |  | 4500
3. Application Development |  |  |  | 45500 | 18.12%
3.1 UI/UX Design | 90 | 90 | 8100
3.2 Mobile app frontend development | 120 | 95 | 11400
3.3 Mobile backend development
3.3.1 Develop API services for mobile integration | 120 | 100 | 12000
3.3.2 Implement database connections | 100 | 100 | 10000
3.0a Mobile Dev Software Licenses & Emulators |  |  | 4000
4. Infrastructure Implementation |  |  |  | 75100 | 29.91%
4.1 Network infrastructure setup | 60 | 110 | 6600
4.2 IoT sensor calibration and implementation
4.2.1 Adjust sensors for environmental conditions | 50 | 90 | 4500
4.2.2 AI integration with IoT sensors | 50 | 100 | 5000
4.3. Cloud-based backend implementation
4.3.1 Implement database and cloud infrastructure setup | 50 | 110 | 5500
4.3.2 Deploy backend services | 70 | 100 | 7000
4.4 API integration | 50 | 100 | 5000
4.5 Purchase and deploy IoT sensors | 15 | 100 | 1500
4.0a IoT Sensors, Network Equipment & Cloud Infrastructure |  |  | 40000
5. Testing and Optimization |  |  |  | 39340 | 15.67%
5.1 Prototyping for stakeholders and users | 80 | 90 | 7200
5.2 Beta testing | 80 | 100 | 8000
5.3 Performance optimization
5.3.1 Load testing | 40 | 90 | 3600
5.3.2 Security penetration testing | 45 | 100 | 4500
5.3.3 Latency and response time optimization | 40 | 90 | 3600
5.4 Deployment and go-live
5.4.1 Deploy system to production environment | 20 | 120 | 2400
5.4.2 Conduct post–deployment monitoring | 56 | 90 | 5040
5.0a Load & Security Testing Tools |  |  | 5000
6. Project closure |  |  |  | 13240 | 5.274%
6.1 Final system review | 24 | 100 | 2400
6.2 Post-launch training and Documentation
6.2.1 Provide training session for operators and staff | 24 | 100 | 2400
6.2.2 Deliver system operation manuals and troubleshooting | 24 | 100 | 2400
6.3 Final report and lessons learned
6.3.1 Document challenges and solutions | 24 | 95 | 2280
6.3.2 Present final project performance evaluation | 8 | 95 | 760
6.0a Hosting, Backups & Training Software |  |  | 3000
Total project cost estimate |  |  |  | 251050
* See software development estimate
Total project cost estimate |  |  |  | 251050

## Labor Estimate - Software Dev
* Software development
Contractor labor estimate | 500 | 100 | 50000
Project team member estimate | 688 | 75 | 51600
Total labor estimate |  |  | 101600
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 10 | 5 | 50
External interface files | 4 | 4 | 16
External outputs | 3 | 5 | 15
External queries | 4 | 5 | 20
Logical internal tables | 6 | 7 | 42
Total function points |  |  | 143
Java 2 languange equivalency value |  |  | 43
Source lines of code (SLOC) estimate |  |  | 6149
Productivity *KSLOC^Penalty (person months) | 27.0318
Total labor hours (160 hours/month) | 4325.0932
Cost/labor hour ($120/hour) | 120
Total software development estimate | 519011.1844

## EV Analysis
Earned Value Calculations for Smart Parking Management Project
Prepared by: All task no Chill |  |  | Date: 2025/03/31
Note: Change the entries to meet your project needs.
Also make sure the formulas work properly based on the data you enter.
[13 empty] | To Date | Planned | Actual
WBS Items | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | PV | % Complete | % Complete | RV | EV
Define the project Scope and objectives | Feb: 2000; Mar: 2000; To Date PV: 4000 | 100 | 100 | 100% | 4000
Market analysis | Mar: 2700; To Date PV: 2700 | 100 | 100 | 100% | 2700
User survey | Mar: 2700; To Date PV: 2700 | 100 | 100 | 100% | 2700
Identify Key Risk Indicators | Mar: 3600; To Date PV: 3600 | 100 | 100 | 100% | 3600
Develop initial project timeline | Mar: 3600; To Date PV: 3600 | 100 | 100 | 100% | 3600
Establish project governance structure | Mar: 3700; Apr: 300; To Date PV: 4000 | 100 | 100 | 100% | 4000
Define risk managment plan | Apr: 3600; To Date PV: 3600 | 100 | 100 | 100% | 3600
Develop recource allocation | Apr: 4000; To Date PV: 4000 | 100 | 100 | 100% | 4000
Identify and document functional requirements | Apr: 2700; To Date PV: 2700 | 100 | 100 | 100% | 2700
Identify and document non-functional requirements | Apr: 2700; To Date PV: 2700 | 100 | 100 | 100% | 2700
Validate requirements with stakeholders | Apr: 2500; To Date PV: 2500 | 100 | 100 | 100% | 2500
Identify required data entities and relationships | Apr: 2375; To Date PV: 2375 | 100 | 100 | 100% | 2375
Design an entity-relationship diagram | Apr: 2375; To Date PV: 2375 | 100 | 100 | 100% | 2375
Choose the database technology | Apr: 1710; To Date PV: 1710 | 100 | 100 | 100% | 1710
Create system architecture diagram | Apr: 1320; May: 2680; To Date PV: 4000 | 100 | 100 | 100% | 4000
API design | May: 8400; To Date PV: 8400 | 100 | 100 | 100% | 8400
Implement user authentication | Apr: 3600; To Date PV: 3600 | 100 | 100 | 100% | 3600
Apply data encryption | Apr: 2400; To Date PV: 2400 | 100 | 100 | 100% | 2400
Establish disaster recovery and backup strategies | Apr: 2400; To Date PV: 2400 | 100 | 100 | 100% | 2400
Define AI use cases | May: 3850; To Date PV: 3850 | 100 | 100 | 100% | 3850
Collect and clean historical parking data | May: 3520; To Date PV: 3520 | 100 | 100 | 100% | 3520
Integration with payment gateway | May: 2640; To Date PV: 2640 | 100 | 100 | 100% | 2640
Database & Design Tool Licenses | Apr: 4500; To Date PV: 4500 | 100 | 100 | 100% | 4500
UI/UX Design | Apr: 7600; May: 500; To Date PV: 8100 | 100 | 100 | 100% | 8100
Mobile app frontend development | May: 11400; To Date PV: 11400 | 100 | 100 | 100% | 11400
Develop API services for mobile integration | May: 12000; To Date PV: 12000 | 100 | 100 | 100% | 12000
Implement database connections | May: 10000; To Date PV: 10000 | 100 | 100 | 100% | 10000
Mobile Dev Software Licenses & Emulators | Apr: 1500; May: 1000; Jun: 1000; Jul: 500; To Date PV: 2500 | 100 | 100 | 100% | 2500
Network infrastructure setup | May: 6600; To Date PV: 6600 | 100 | 100 | 100% | 6600
Adjust sensors for environmental conditions | May: 4500; To Date PV: 4500 | 100 | 100 | 100% | 4500
AI integration with IoT sensors | May: 2500; Jun: 2500; To Date PV: 2500 | 100 | 100 | 100% | 2500
Implement database and cloud infrastructure setup | May: 5500; To Date PV: 5500 | 100 | 100 | 100% | 5500
Deploy backend services | May: 7000; To Date PV: 7000 | 100 | 100 | 100% | 7000
API integration | May: 5000; To Date PV: 5000 | 100 | 70 | 70% | 3500
Purchase and deploy IoT sensors | Jun: 1500; To Date PV: 0 | 0 | - | 0% | 0
IoT Sensors, Network Equipment & Cloud Infrastructure | May: 20000; Jun: 20000; To Date PV: 20000 | 100 | 100 | 100% | 20000
Prototyping for stakeholders and users | May: 7200; To Date PV: 7200 | 100 | 60 | 60% | 4320
Beta testing | May: 1200; Jun: 6800; To Date PV: 1200 | 100 | 10 | 10% | 120
Load testing | Jun: 3600 | 0 | 0 |  | 0
Security penetration testing | Jun: 4500 | 0 | 0 |  | 0
Latency and response time optimization | Jun: 3000; Jul: 600; To Date PV: 0 | 0 | 0 |  | 0
Deploy system to production environment | Jul: 2400 | 0 | 0 |  | 0
Conduct post-deployment monitoring | Jul: 5040 | 0 | 0 |  | 0
Load & Security Testing Tools | Jun: 3000; Jul: 2000
Final system review | Jul: 2400 | 0 | 0 |  | 0
Provide training session for operators and staff | Jul: 2400 | 0 | 0 |  | 0
Deliver system operation manuals and troubleshooting guides | Jul: 2400 | 0 | 0 |  | 0
Document challenges and solutions for future improvement | Jul: 2280 | 0 | 0 |  | 0
Present final project performance evaluation | Jul: 760 | 0 | 0 |  | 0
Hosting, Backups & Training Software | May: 500; Jul: 2500
Monthly Planned Value (PV) | 0 | 2000 | 18300 | 45580 | 115490 | 45900 | 23280 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 175910
Cumulative Planned Value (PV) | Jan: 0; Feb: 2000; Mar: 20300; Apr: 65880; May: 181370; Jun: 227270; Jul: 250550
Monthly Actual Cost (AC) | Feb: 19000; Mar: 38000; Apr: 47500; May: 54000
Cumulative Actual Cost (AC) | Jan: 0; Feb: 19000; Mar: 57000; Apr: 104500; May: 158500
Monthly Earned Value (EV) | Jan: -; Feb: 2000; Mar: 18300; Apr: 45580; May: 110030
Cumulative Earned Value (EV) | Jan: 0; Feb: 2000; Mar: 20300; Apr: 65880; May: 175910
Project EV as of May 31 | Jan: 175910
Project PV as of May 31 | Jan: 181370
Project AC as of May 31 | Jan: 158500
CV=EV-AC | Jan: 17410
SV=EV-PV | Jan: -5460
CPI=EV/AC | Jan: 111%
SPI=EV/PV | Jan: 96.99%
Estimate at Completion (EAC) | Jan: 225752.7997; Feb: (original plan of $250,550 divided by CPI)
Estimated time to complete | Jan: 6.1862; Feb: (original plan of 6 months divided by SPI)